## Sheet1
Comment Number | Sub Comment Ref: | ADC Latest Response/Query | BDW Southampton Response | Supporting Documentation | Notes
18. (formally 25) | 1 | What groundwater level is the puddled clay design based on? Historic monitoring suggests very shallow depths. | In order to answer the question posed we first must discuss the principle of the supporting geotechnical evidence provided with the RSK Technical Note. The summary of said report confirm that the water strikes & "seepages" noted within the logs from the intrusive borehole and trial pit data, confirm that the site does not exhibit a continuous high groundwater. Instead, the recorded water is defined as perched water within discrete granular layers of overlying sands and gravels above the London Clay formation, and in isolated pockets within the London Clay itself. It is this definition which supports the proposal for a puddled clay liner for the attenuation basins. See below additional supporting citations on the definitions of Groundwater: Environment Agency – Groundwater Definition “Groundwater is defined as all water which is below the surface of the ground in the saturation zone and in direct contact with the ground or subsoil.” (Environment Agency – Protect Groundwater and Prevent Groundwater Pollution) Source [gov.uk] The BGS then expand on common terminology associated with Groundwater and cite Water Table as per below extract. British Geological Survey (BGS) Groundwater Level Terminology “Groundwater level is a term that is used in a relatively loose way, normally referring to the level, either below ground or above ordnance datum, at which soil or rock is saturated. This is also referred to as the water table and represents the top of the saturated zone. Above the water table lies the unsaturated zone.” (British Geological Survey – Groundwater Level Terminology) Source [www2.bgs.ac.uk] BGS then further define Perched Water as per below: British Geological Survey (BGS) – Perched Water Definition “Perched water tables occur when there are lenses of impermeable material in a rock that is otherwise permeable. These allow small localised water tables to develop over the lenses, which can overlay a regional water table in the surrounding rock mass.” (British Geological Survey – Groundwater Level Terminology) Source [www2.bgs.ac.uk] The BGS definition had drawn us to the conclusion that perched water (unsaturated zone, localised) is different to true groundwater (saturation zone, continuous). BDW have evidence from intrusive boreholes/trial pits which have shown water within the unsaturated Zone thus we deem this not to be groundwater as BGS describe. On this basis, the assumption that puddled clay will provide an effective liner is considered technically sound and consistent with the site’s hydrogeological conditions. | Site investigation works (Trial Pits and Borehole Logs): J202433 Barnham CP1-CP3 Logs J202433 Barnham CP101-CP102 Logs Tars Farm Site Plan - Bridge Boreholes composite plan
| 2 | Provide design for distribution trench. Where will the water collected by the land drainage system go? | Design of the distribution trench is shown on the detail on Dwg 228_P2. Detail label updated to say ‘Typical Land Drainage Trench & Distribution Trench’. Water collected will drain down to the topographically lower distribution trench where flows will surcharge to ground level and spill overland where it will infiltrate through the unsaturated layer of topsoil’s and into the downstream watercourse, mimicking the greenfield runoff regime.
| 3 | Final testing results required. | See updated RSK Technical note now with laboratory test results appended within Appendix F
| 4 | Final earthworks specification required. | The earthworks specification is outlined within the attached RSK Technical Note sections 5 & 6. Note the placement and compaction of the clay material ,as shown on MJA drawing DWG 213-P3, is to be undertaken in accordance with DMRB Series 600 specification, thus the layer thickness and compaction regime/No. of passes will be determined by the specific equipment being used by the contractor. It is not deemed necessary nor practical at this time to confirm the machinery specification, this however will noted on the verification report produced by RSK (or other suitably qualified consultant) on completion of the works and verified as in accordance with the requirements as outlined within the RSK technical note.
| 5 | Appears to be a preliminary design and only refers to basins, swale is not included. | Swale and basin designs with reference to the RSK produced technical note Ref:19424061 are shown on detail ref: Dwg 213-P3. These are not preliminary designs and should be considered as a construction drawing
| 6 | How is 5m thick puddled clay achieved under the basin? | As noted within the commentary to point 1 above the deep borehole data collected to date has shown that consistent London Clay strata is present from circa 1.9m below existing ground level to depths up to 30m. On excavation of the proposed basin to formation level ,which sits circa 2m below existing levels, all sand and gravel layers noted within the borehole date will be removed leaving only the London clay strata to the depths noted above. The surface layer of the exposed London Clay will then be puddled. All data be it either deep borehole or trial pitting within the immediate area of the proposed basins confirm the uniformity of the London clay material. All above referenced within the RSK Technical Note. | Site investigation works (Trial Pits and Borehole Logs): J202433 Barnham CP1-CP3 Logs J202433 Barnham CP101-CP102 Logs Tars Farm Site Plan - Bridge Boreholes composite plan
| 7 | What is the factor of safety on the design of the 5m thickness and how has the 5m thickness been determined? | See note above
| 8 | It is “assumed” only London clay from the site will be used. This should be specified not an assumption. | RSK technical note updated, see section 4 which now refers too: Only excavated London clay will be re-used on site as part of the proposed attenuation pond/swale construction works
| 9 | Excavation method is not detailed on the Basin Construction Detail. | Excavation method is noted within the RSK Technical note and now added to the Basin and Swale construction detail ref: DWG 213-P3 |  | Excavation method is a construction methodology and should not be a material consideration within this discharge of condition requiring "full details of the proposed surface water drainage scheme"
| 10 | RSK Specification is not referred to on the Basin Construction Detail. | Excavation method is noted within the RSK Technical note and now added to the Basin and Swale construction detail ref: DWG 213-P3
| 11 | Suggest verification monitoring/sign off is undertaken by RSK not the contractor. | BDW will appoint RSK (or another suitably qualified consultant) to undertake verification monitoring and sign-off for the attenuation basin works. The appointed consultant will: Attend a pre-start meeting with the groundworks contractor to relay and confirm the earthworks specification and design requirements. Provide a watching brief during excavation and subsequent earthworks stages to ensure compliance with the approved methodology. Prepare and issue a formal verification report upon completion, confirming that the installation aligns with the earthworks specification and design. This approach ensures independent oversight and robust quality assurance in accordance with ADCs request |  | Verification and monitoring of the construction works should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 12 | How is the silt treatment being implemented (e.g. location, size/design of tank) Plan required together with full details of the products that are to be used. | Groundwater Ingress and Silt Management Plan updated to now include for plan showing location of Silt treatment equipment and location for discharge. Product references provided and appended to said plan. | Groundwater Ingress and Silt Management Plan Rev A.pdf | Management of the construction works and any subsequent water management and silt separation works should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 13 | Where is the dewatering discharge location? | As Above - Groundwater Ingress and Silt Management Plan updated to now include for plan showing location of Silt treatment equipment and location for discharge. Product references provided and appended to said plan. | Groundwater Ingress and Silt Management Plan Rev A.pdf
| 14 | There should be no discharge from the dewatering system during rainstorms otherwise GFRO rate is exceeded | Groundwater Ingress and Silt Management Plan updated to include note to confirm no discharge/dewatering activities will take place during rainstorm events | Groundwater Ingress and Silt Management Plan Rev A.pdf
8. (formally 10) | 1 | There are inconsistencies between the manhole schedules and drawing 210-C1. See comment 34 | Manhole and Pipe between spare SW47Ctrl manhole and Tank 1 removed on dwg 210-C2. Inconsistencies corrected on manhole schedule 705-T9. These were specifically cover levels for HD3, HD4 & HD5. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
9. (formally 11) | 1 | There are inconsistencies between the manhole schedules and drawing 210-C1. See comment 34 | Manhole and Pipe between spare SW47Ctrl manhole and Tank 1 removed on dwg 210-C2. Inconsistencies corrected on manhole schedule 705-T9. These were specifically cover levels for HD3, HD4 & HD5. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
22. (formally 29) | 1 | Please demonstrate that the proposed measures to prevent groundwater ingress around the headwalls are sufficient to resist groundwater pressure. | Refer to RSK Technial Note (RSK ref:19424061 November 2025) for statement on the level and nature of the perched groundwater in relation to groundwater pressures.
| 2 | Please provide a detail showing how and where the bentonite powder is to be placed. | A detail has been added to Dwg 213 -P3 showing basin inlet headwall and bentonite placement.
23. (formally 30) | 1 | See comment 18 | As above
31. (formally 39) | 1 | Please provide the larger scale sheets | Larger sheets are now provided on dwgs 001-T12, 002-T9, 003-T8 and 011-T3. Note dwg 004 ‘Overall Site engineering’ has been removed as deemed not necessary given the larger scale sheets |  | The overall plan provided is at a recognised scale and in PDF format that should be legible, we do not consider this to be a reason for refusal
| 2 | There appears to be clashes between SW drainage and landscaping at the following locations: Side of Plot 190 Side of Plot 193 Rear of 159 Front 162 &163 Parking bay 140 Parking bays 103/105 Parking bay 87/88 Rear of plot 122 | All clashes noted within ADC response have been reviewed and all clashes removed, in some instances this has meant the removal or reduction of the tree/shrub. A discussion has been undertaken with the ADC landscape officer (copy attached) which states all the adjustments as part of this exercise will be picked up as part of an Non-material amendment application once this condition has been satisfied. In addition those trees remaining the specification of tree/shrub species has been reviewed and we can confirm all those located in relative close proximity to drainage are deemed not to have potential to cause damage or that requires any specific root protection barriers given the specified tree and its anticipated root growth/pattern. | Landscaping Email Correspondence.pdf
| 3 | Please provide a revised landscape proposal or demonstrate measures are in place to prevent the trees/landscaping damaging the drainage. | See above:
34. (formally 42) | 1 | Drg 210-C1: Tank 1 Outlet is noted as 300 diameter and 225 diameter | Manhole and Pipe between spare SW47Ctrl manhole and Tank 1 removed on dwg 210-C2 thus the noted conflicting information is no longer applicable. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 2 | Both chambers noted as SWCTRL47 (should there only be 1 chamber?) | Chamber SW47Ctrl on Dwg 210-C2 is labelled as flow control chamber and reflects the updated section through the chamber. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 3 | SW47CTRL drawn as catchpit but its a flow control chamber | Chamber SW47Ctrl on Dwg 210-C2 is labelled as flow control chamber and reflects the updated section through the chamber. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 4 | Chamber diameter is different to schedule | Manhole diameters updated and on schedule 705-T9. |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 5 | IL on pipe not readable | IL note moved for clarity, see updated drawing ref: on Dwg 210-C2 |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 6 | Sump level of 0.898 appears to be incorrect (not consistent with 500mm deep sump) | Sump level corrected to 0.8mAOD, see updated drawing ref: on Dwg 210-C2 |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 7 | Detail regarding vent is unclear. More detail required. | Vent detail updated to include more detail, see updated drawing ref: on Dwg 210-C2
| 8 | Tank 2 Chamber diameters are different to schedule | All chamber diameters have been corrected, see updated drawing ref: on Dwg 210-C2
| 9 | HD1CTRL IL shown on pipe is different to schedule and above tank base | HD1CTRL IL corrected on updated drawing ref: on Dwg 210-C2 |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 10 | HD1 drawn as catchpit but it is a flow control chamber | HD1 now drawn as a flow control chamber, see updated drawing ref: on Dwg 210-C2 |  | Whilst we acknowledge the discrepancies in the drawings these do not fundamentally impact the surface water drainage scheme and thus should not be a material consideration within this discharge of condition, note the condition wording ""full details of the proposed surface water drainage scheme"
| 11 | Detail regarding vent unclear. More detail required. | Vent detail updated to include more detail, see updated drawing ref: on Dwg 210-C2
6. (formally 10) | 1 | This condition cannot be discharged until the details relating to Condition 8 have been agreed. This is so that the approved drawings can be included in the document. | Noted