Proposed Construction Programme – Southern Allotments, Littlehampton

Overall Duration: -24 weeks

| Phase | Scope of Works | Duration |
| --- | --- | --- |
| 1. Preliminaries & Mobilisation | Site compound & welfare setup, protective fencing, signage, surveys, setting out. | 2 weeks |
| 2. Enabling & Earthworks | Site strip, topsoil storage, bulk earthworks to formation levels, temporary haul routes. | 2 weeks |
| 3. Drainage Infrastructure | Excavate & install soakaway (175m² x 1.2m), manholes, gullies, pipework; connect to existing soakaway. | 4 weeks |
| 4. Roads & Parking Sub-Structure | Construct sub-base, kerbs, edge restraints; form disabled & standard parking bays. | 4 weeks |
| 5. Footpaths & Cycleways | Install hoggin footpaths & cycle routes, maintenance track, edging. | 3 weeks |
| 6. Road & Parking Surfacing | Binder & surface courses (HRA/AC), bay markings, road bollards. | 2 weeks |
| 7. Fencing, Gates & Street Furniture | Security fencing, palisade gates, bollards, Sheffield cycle stands. | 2 weeks |
| 8. Lighting & Services | Install temporary construction lighting (welfare/security), service ducts, utilities connections. | 2 weeks |
| 9. Landscaping & Finishes | Topsoil replacement, planting, biodiversity features (bird boxes, hedgehog homes), reinstatement. | 3 weeks |