Sefter Farm Travel Plan
2026-2030 delivery plan for Travel Plan Coordinator

| Site | Barfoots of Botley Ltd, Sefter Farm Site, Pagham Road |
| --- | --- |
| Planning reference | P/117/21/PL |
| Source document | Formal Travel Plan HTp/2167/TP/01, July 2022 |
| Coordinator | Paul Chilton, Head of Logistics and Planning |
| Delivery period | 2026 to 2030; 2030 is treated as the end-of-plan target year |

Purpose of this working plan This document converts the formal 2022 planning Travel Plan into a concise operational plan for actioning from 2026. It retains the formal objectives, measures, targets and monitoring requirements, but re-baselines the delivery dates so that Year 1 is 2026 and the final targets are for 2030.

# 1. Executive summary

The core aim is to reduce single-occupancy vehicle trips and encourage public transport, cycling, walking and car sharing where practicable. The plan is built around six measurable modal-share targets and a practical action plan covering cycle parking, Cycle to Work, staff minibus/public transport information, car sharing, travel information and campaign activity.

| Theme | Working summary |
| --- | --- |
| Primary outcome | Move from 60% car/van driver baseline to 54% by 2030. |
| Key opportunity | 49% of survey respondents said they would consider car sharing; this supports a targeted car-sharing programme. |
| Existing support | Secure covered cycle parking for 30 cycles and 16 motorcycles is included; Cycle to Work continues to be promoted. |
| Monitoring | Formal staff surveys at the end of 2026, 2028 and 2030, with annual progress reporting to West Sussex County Council Travel Planning Officer. |

# 2. Baseline position from 2022 staff survey

The formal plan uses the April 2022 staff survey as the baseline. It records modal share by main method of travel to work and identifies staff interest in car sharing and active/public transport opportunities.

| Mode | Baseline modal share | Implication |
| --- | --- | --- |
| Car/van as driver | 60% | Primary reduction target |
| Car/van as passenger | 24% | Forms the baseline for car sharing |
| Public transport incl. staff minibus | 8% | Opportunity to promote existing minibus and bus services |
| Pedal cycle | 4% | Supported by secure covered cycle parking and Cycle to Work |
| Motorcycle | 2% | To be retained with 16 covered motorcycle spaces |
| Foot | 2% | To be retained |

# 3. 2026-2030 target dashboard

The formal five-year targets have been mapped to the 2026 start date specified for delivery. Year 1 therefore aligns with the end of 2026, Year 3 with the end of 2028, and Year 5 / end of Travel Plan with the end of 2030.

| No. | Objective | 2022 baseline | End 2026 | End 2028 | End 2030 | Success measure |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Reduce single-occupancy vehicle trips | 60% | 58% | 56% | 54% | Reduce by 6 percentage points |
| 2 | Increase public transport incl. staff minibus | 8% | 9% | 9% | 10% | Increase by 2 percentage points |
| 3 | Increase car sharing | 24% | 25% | 26% | 27% | Increase by 3 percentage points |
| 4 | Retain walking | 2% | 2% | 2% | 2% | Maintain |
| 5 | Increase cycling / active travel | 4% | 5% | 5% | 5% | Increase by 1 percentage point |
| 6 | Retain motorcycle use | 2% | 2% | 2% | 2% | Maintain |
| 7 | Encourage the use of Electric Vehicle | 0% | 1% | 1.5% | 2% | Establish and increase to 2% |

# 4. Delivery workstreams

These workstreams translate the formal action plan into practical tasks for the Coordinator. Items marked "maintain" should be checked and refreshed regularly; items marked "launch" should be prioritised early in 2026.

| Workstream | Coordinator task | Timing | Owner |
| --- | --- | --- | --- |
| Coordinator set-up | Confirm Coordinator contact details, responsibilities, reporting route and working time allocation. | 2026 launch; maintain through 2030 | Paul Chilton / Developer |
| Travel information hub | Create and maintain a noticeboard or equivalent staff information point with walking, cycling, public transport, minibus and car sharing information. | 2026 launch; update as appropriate | Travel Plan Coordinator |
| Cycle parking | Confirm secure, covered parking provision for 30 cycles and make sure it is visible, accessible and communicated to staff. | 2026 launch; annual check | Developer / Coordinator |
| Cycle to Work | Provide practical staff guidance on accessing Cycle to Work, including e-bikes. | 2026 launch; refresh annually | Travel Plan Coordinator |
| Car sharing | Promote car sharing and provide an internal method for staff to connect with compatible routes and shifts; include West Sussex Lift Share information. | 2026 launch; refresh quarterly | Travel Plan Coordinator |
| Public transport and minibus | Promote staff minibus provision, subsidised Stagecoach routes and shift-compatible routes in staff communications. | 2026 launch; refresh at timetable changes | Travel Plan Coordinator |
| Campaigns | Use national and local campaigns to remind staff of sustainable travel options. | Ongoing | Travel Plan Coordinator |
| Monitoring and reporting | Run modal-share surveys at end of years 1, 3 and 5; review progress annually and submit monitoring reports as required. | 2026, 2028, 2030 surveys; annual reporting | Travel Plan Coordinator |

# 5. Year-by-year action plan

| Year | Priority actions |
| --- | --- |
| 2026 - Year 1 | Launch plan, staff communications, noticeboard, car-share matching route, Cycle to Work guidance, minibus/public transport promotion. Confirm TPC details with the Council. Complete Year 1 staff travel survey and report progress against end-2026 targets. |
| 2027 - Year 2 | Keep information live, refresh campaign messages, check cycle/motorcycle facilities, review car-share/minibus uptake indicators, prepare remedial actions if Year 1 targets are off track. |
| 2028 - Year 3 | Repeat staff travel survey. Compare results with end-2028 targets. Adjust promotion and operational support where modes are below target. |
| 2029 - Year 4 | Maintain measures, refresh staff engagement, continue annual reporting and prepare for final survey. Focus on any gaps to the 2030 targets. |
| 2030 - Year 5 | Complete final staff travel survey and end-of-plan review. Report final performance against 2030 targets and recommend whether measures should continue as business-as-usual. |

# 6. Monitoring framework and evidence log

The formal plan requires monitoring over five years, including surveys at the end of Years 1, 3 and 5, with annual monitoring reports submitted to West Sussex County Council Travel Planning Officer. The table below is designed to be updated during delivery.

| KPI / evidence area | What to capture | Frequency | Evidence |
| --- | --- | --- | --- |
| Modal share survey | Employee travel survey using consistent questions to monitor main mode of travel | End 2026, 2028 and 2030 | Survey response count; modal share percentages |
| Car sharing | Participation/interest log and communications evidence | Quarterly review | Number of registrations or matched opportunities; staff communications issued |
| Cycle use | Cycle parking observations and Cycle to Work promotion record | Quarterly/seasonal review | Cycle spaces used; Cycle to Work communications issued |
| Public transport/minibus | Promotional material and timetable information checks | At timetable changes and annually | Information current; staff awareness messages issued |
| Noticeboard/information hub | Photographic or dated record of updates | Monthly check | Information current and prominently displayed |
| Annual report | Short report covering actions completed, survey results where available, issues and next steps | Annually | Submitted as required |

# 7. Coordinator checklist

| No. | Action | Done |
| --- | --- | --- |
| 1 | Confirm and record Travel Plan Coordinator contact details for Council records. |  |
| 2 | Create a simple Travel Plan folder holding the source plan, surveys, actions, evidence and reports. |  |
| 3 | Build a staff communications pack: noticeboard, posters, induction slide/email and manager briefing. |  |
| 4 | Set up a car-share matching route or internal platform suitable for shift patterns and local commute clusters. |  |
| 5 | Confirm Cycle to Work guidance and ensure e-bike availability is clearly communicated. |  |
| 6 | Validate cycle and motorcycle parking provision and check signage/accessibility. |  |
| 7 | Create the 2026 survey template using the same modal categories as the 2022 baseline. |  |
| 8 | Prepare annual progress report structure before the first reporting cycle. |  |